## Hoja1
Course | Task | Duration Days | Beginning Date | Due Date | Hs/Tarea | Acumuladas
Introduction to Website Development | 1: Create an Initial Website Mockup |  |  | 3 | 1-abr.-2019 | 4-abr.-2019 | 24 | 24
| 2: Add Style to the Website with CSS |  |  | 3 | 8-abr.-2019 | 11-abr.-2019 | 24 | 48
| 3: Present Data in Lists and Tables |  |  | 3 | 11-abr.-2019 | 17-abr.-2019 | 24 | 72
| 4: Add Forms and Maps |  |  | 2 | 17-abr.-2019 | 25-abr.-2019 | 16 | 88
|  |  | 11 | Team code review |  |  | 0 | 25-abr.-2019 | 25-abr.-2019 | 0 | 88
Introduction to JavaScript Development | 1: Get Started with JavaScript |  |  | 3 | 25-abr.-2019 | 6-may.-2019 | 24 | 112
| 2: Access and Display Public Data |  |  | 5 | 6-may.-2019 | 20-may.-2019 | 40 | 152
| 3: Calculate and Display Statistics |  |  | 5 | 22-may.-2019 | 5-jun.-2019 | 40 | 192
| 4: Access Live Public Data with jQuery/AJAX |  |  | 4 | 5-jun.-2019 | 19-jun.-2019 | 32 | 224
|  |  | 17 | Team code review |  |  | 0 | 19-jun.-2019 | 19-jun.-2019 | 0 | 224
Extra Task | Json exercises |  |  | 0 |  |  | 0 | 224
Introduction to Mobile Web Development | 1: Design UI for Game Schedule App |  |  | 1 | 19-jun.-2019 | 20-jun.-2019 | 8 | 232
| 2: Implement the Schedule App |  |  | 5 | 20-jun.-2019 | 4-jul.-2019 | 40 | 272
| 3: Improving the Schedule App |  |  | 2 | 10-jul.-2019 | 11-jul.-2019 | 16 | 288
| 4: Add Live Data |  |  | 5 | 15-jul.-2019 | 29-jul.-2019 | 40 | 328
|  |  | 13 | Team code review |  |  | 0 | 29-jul.-2019 | 29-jul.-2019 | 0 | 328
Extra Task | Java Introduction exercices |  |  | 0 |  |  | 0 | 328
Introduction to Java 1 | 1: Set Up Project, Implement Players |  |  | 3 | 29-jul.-2019 | 7-ago.-2019 | 24 | 352
| 2: Implement Games |  |  | 2 | 7-ago.-2019 | 12-ago.-2019 | 16 | 368
| 3: Implement Ships |  |  | 4 | 14-ago.-2019 | 26-ago.-2019 | 32 | 400
| 4: Implement Salvoes |  |  | 2 | 26-ago.-2019 | 30-ago.-2019 | 16 | 416
|  |  | 15 | 5: Implement Scores |  |  | 4 | 2-sep.-2019 | 13-sep.-2019 | 32 | 448
Introduction to Java 2 | 1: Implement player login |  |  | 5 | 13-sep.-2019 | 27-sep.-2019 | 40 | 488
| 2: Add joining and creating games |  |  | 5 | 30-sep.-2019 | 16-oct.-2019 | 40 | 528
| 3: Add placing ships |  |  | 6 | 16-oct.-2019 | 1-nov.-2019 | 48 | 576
| 4: Add firing salvos |  |  | 4 | 4-nov.-2019 | 13-nov.-2019 | 32 | 608
| 5: Add hits and sinks |  |  | 6 | 15-nov.-2019 | 2-dic.-2019 | 48 | 656
|  |  | 32 | 6: Implement logic for game play |  |  | 6 | 4-dic.-2019 | 20-dic.-2019 | 48 | 704
[7 empty] | 88 |  |  | 704